## April 2026
Date | Task Name | Hours | Notes | Ticket Number
01-04-2026 | Q1 2026 Solar Energy Production Data Extraction - Extracted solar energy production data for all sites covering January February and March using Tesla API | 9 | Sprint 4 - Created by Shuai | #13804
02-04-2026 | Q1 Data Processing and Validation - Formatted and validated extracted solar production data for completeness and accuracy | 9 | Sprint 4 | #13804
03-04-2026 | India Public Holiday | 0
04-04-2026 | Weekend | 0
05-04-2026 | Weekend | 0
06-04-2026 | Q1 Data Delivery - Finalized and delivered Q1 2026 solar energy production dataset to stakeholders | 9 | Sprint 4 | #13804
07-04-2026 | New Sites Solar Data Extraction - Extracted solar energy production data for new sites list provided by Shuai | 9 | Sprint 4 - Created by Shuai | #14806
08-04-2026 | New Sites Data Processing - Formatted and validated solar production data for new sites using Tesla API integration | 9 | Sprint 5 | #14806
09-04-2026 | New Sites Data Delivery - Completed extraction and delivered solar production dataset for new sites to stakeholders | 9 | Sprint 5 | #14806
10-04-2026 | sqTelemetry Table Design - Designed table schema with all required columns and data label fields for SQMD data support | 9 | Sprint 5 - Created by Shuai | #14469
11-04-2026 | Weekend | 0
12-04-2026 | Weekend | 0
13-04-2026 | DSGS 15-Min Interval Data Export - Extracted 15-minute interval data from batteries enrolled in DSGS program | 9 | Sprint 5 - Created by Shuai | DSGS Export
14-04-2026 | DSGS Data Formatting and Validation - Processed and validated 15-min interval battery data for DSGS export requirements | 9 | Sprint 5 | DSGS Export
15-04-2026 | DSGS Export Delivery and sqTelemetry Table Creation - Delivered DSGS export data and created sqTelemetry table in DEV environment | 9 | Sprint 5 | #14469
16-04-2026 | sqTelemetry Data Copy - Copied 1-2 days worth of data from silverCommDataSite to sqTelemetry table | 9 | Sprint 5 | #14469
17-04-2026 | sqTelemetry Data Verification - Verified data exists and matches between silverCommDataSite and sqTelemetry tables | 9 | Sprint 5 | #14469
18-04-2026 | Weekend | 0
19-04-2026 | Weekend | 0
20-04-2026 | getAllVppSitesByUserId Filtering Implementation - Implemented server-side filtering logic for multiple fields and operators | 9 | Sprint 4 | #10357
21-04-2026 | Filtering Logic Testing - Tested dynamic filtering functionality with various field combinations and filter operators | 9 | Sprint 4 | #10357
22-04-2026 | Sorting Implementation - Developed server-side sorting functionality supporting any field with ascending and descending order | 9 | Sprint 4 | #10357
23-04-2026 | Sorting Logic Testing - Validated dynamic sorting across different fields and verified correct data ordering | 9 | Sprint 4 | #10357
24-04-2026 | Global Search Implementation - Implemented global search functionality to search across all site fields | 9 | Sprint 4 | #10357
25-04-2026 | Weekend | 0
26-04-2026 | Weekend | 0
27-04-2026 | Search Testing and Integration - Tested global search with filtering and sorting integration and verified results | 9 | Sprint 4 | #10357
28-04-2026 | Postgres Database Enhancement - Added optimization_enabled and optimization_schedule columns to tb_bas_program_info table | 9 | Sprint 5 | #14782
29-04-2026 | Postgres Migration Testing - Executed ALTER TABLE commands in DEV environment and verified schema changes | 9 | Sprint 5 | #14782
30-04-2026 | Final Testing and Documentation - Completed testing for Sprint 4 and Sprint 5 tasks and prepared documentation for deployment | 9 | Sprint 5 | #10357, #14782